## Slide 1: Project Charter: OPIM5270 1/2
Case for change / Problem Statement
Not understanding the business need in perspective of a project manager. What will I do with this knowledge as a fresher, I won’t be working in the managerial position.
Business Case
Project Management class is required for the MSBAPM program As for the career perspective, I might use the knowledge gained from this class as a company project manager to advance into a managerial position.
In Scope | Out of Scope
Attending all the lectures | Covering advanced topics
Learning PM Fundamentals | Learning Agile methodology
Practicing the provided tools | Out of syllabus exam questions
Taking timely exams and passing | 
Constraint Matrix (Priority Matrix) |  |  | 
 | MOST | SOME | LEAST
SCOPE |  | X | 
TIME | X |  | 
COST |  | X | 
Top Risks (max. 5)
Won’t learn anything out of it Less grades will impact academic future Failing the course, taking the course again will be expensive.
Objectives / Goal statements
Completing the course Gain knowledge about project management and managerial skills. Understanding concepts that otherwise you would neglect while working as a project manager.
Assumptions
It will be an in-person class Participation is a must Practicing is as important as participation
Date of Charter

## Slide 2: Project Charter: OPIM5270 2/2
Incoming Dependency | Outgoing Dependency
MSBAPM Acceptance | Passing the exam
Prepaid Fees | Attendance and Participation
Undergraduate Degree | 
Course availability | 
Deliverables & Milestones (High Level Milestone Plan) |  |  | 
Project Start Date: 08/29/2023 |  | Project End Date: 12/05/2023 | 
Key Deliverable | Milestone Name (MN) |  | Planned MS Date
Test 1 | OPIM5270 – Week 4 |  | 09/19/2023
Test 2 (Midterm) | OPIM5270 – Week 6 |  | 10/03/2023
Test 3 (Finals) | OPIM5270 – Week 12 |  | 11/14/2023
Discussion 1 | OPIM5270 – Week 5 |  | 09/26/2023
Discussion 2 | OPIM5270 – Week 9 |  | 10/24/2023
Discussion 3 | OPIM5270 – Week 12 |  | 11/14/2023
Project Scenario | OPIM5270 – Week 15 |  | 12/05/2023
Signoff |  | 
Role | Signature | Date
Sponsor |  | 
PSB Member |  | 
PSB Member |  | 
PSB Member |  | 
PSB Member |  | 
PSB Member |  | 
Beneficiary |  | 
Beneficiary |  | 
Project Organization | 
Sponsor | Rohit Akole
Steering Board Members (PSB) | Prof. Christopher Field
Project Manager | 
Workstream Leaders | 
Team Members | 
Project Costs (USD) |  | 
Total: 4500 | Internal: 4000 | External: 500
Project Benefits |  | 
NPV: | IRR: | Break Even:
Indirect Benefits: |  | 
Notes: IRR: Internal Rate of Return
NPV: Net Present Value